📝Test Estimation Report

## 1. Introduction

This document provides an estimation of testing effort, resources, and timelines for the upcoming release of the web application. The estimation covers both Functional and Non-Functional Testing activities. It also highlights assumptions, risks, and dependencies considered during estimation.

## 2. Objectives

- Provide effort and resource estimates for Functional and Non-Functional testing.

- Define the scope and assumptions for estimation.

- Identify risks and mitigation plans related to testing effort.

- Establish a baseline for test planning and execution.

## 3. Scope of Testing

### 3.1 Functional Testing

- Requirement Validation

- Test Case Design & Review

- Functional Test Execution

- Regression Testing

- Defect Reporting & Retesting

### 3.2 Non-Functional Testing

- Performance & Load Testing

- Security Testing

- Compatibility (Cross-Browser & Device) Testing

- Usability Testing

- Accessibility Testing

## 4. Estimation Approach

The following methods were used:

- Work Breakdown Structure (WBS) – breaking down into granular tasks.

- Historical Data – based on past project velocity & defect density.

- Three-Point Estimation (PERT Formula) – for uncertain activities.

- Expert Judgment – input from QA leads and SMEs.

## 5. Estimation Breakdown

### 5.1 Functional Testing Estimation

| Activity | Effort (Person-Days) | Assumptions |
| --- | --- | --- |
| Requirement Analysis | 5 | All requirements are documented & reviewed. |
| Test Case Preparation | 10 | ~200 test cases to be written. |
| Test Case Review | 3 | Peer review for coverage & quality. |
| Test Execution | 15 | Includes multiple cycles & retesting. |
| Defect Reporting & Closure | 5 | Avg. 30 defects expected. |
| Regression Testing | 7 | Regression pack ~150 test cases. |
| Total | 45 Person-Days |  |

### 5.2 Non-Functional Testing Estimation

| Activity | Effort (Person-Days) | Assumptions |
| --- | --- | --- |
| Performance & Load Testing | 10 | Using JMeter; 1,000 concurrent users. |
| Security Testing | 8 | Includes vulnerability scanning + manual pen tests. |
| Compatibility Testing | 5 | Across 3 browsers & 2 devices. |
| Usability Testing | 3 | Involves 5 business users for feedback. |
| Accessibility Testing | 4 | WCAG 2.1 compliance checks. |
| Total | 30 Person-Days |  |

## 6. Resource Plan

| Role | Count | Duration | Effort Allocation |
| --- | --- | --- | --- |
| QA Manager | 1 | Full cycle | Oversight, reporting, sign-off |
| Test Leads | 1 | Full cycle | Planning, reviews, defect triage |
| Test Engineers | 3 | Full cycle | Execution of functional test cases |
| Performance Tester | 1 | 2 weeks | Performance & load testing |
| Security Engineer | 1 | 1.5 weeks | Security assessment |

## 7. Effort Summary

- Functional Testing Effort: 45 Person-Days

- Non-Functional Testing Effort: 30 Person-Days

- Total QA Effort: 75 Person-Days

## 8. Assumptions

- Requirements are signed off and stable.

- Test environments will be available as per schedule.

- Test data will be prepared by the development/business team.

- All third-party integrations are stable.

- No major scope changes post-estimation.

## 9. Risks & Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Delayed environment readiness | High | Request early provisioning; fallback to lower env. |
| Scope creep in requirements | Medium | Re-baseline estimation after CR approval. |
| Limited performance testing window | High | Early performance testing cycles; monitoring post go-live. |
| Test data unavailability | Medium | Use synthetic data generation tools. |

## 10. Conclusion & Recommendation

Based on the estimation approach and breakdown, a total of 75 Person-Days effort is required to complete both Functional and Non-Functional testing activities. Adequate resource allocation, stable environments, and timely data availability are critical for meeting this estimation.

Prepared By:
QA Manager – _____________________
Date – _____________________